## Sheet1
Goals | Task/ Deliverables | Estimated Time | Person Responsible
Pre Event Planning + Setup |  | 07/10/23 - 08/10/23 | Sowmya Mutya, Lakshmi Anusha & Renee Ashby
| Define Project Scope and Objectives | 07/11/23 - 07/18/23 | Sowmya Mutya, Lakshmi Anusha & Anyass Ibrahim
| Assemble Project Team | 07/10/23 - 07/15/23 | Sowmya Mutya & Lakshmi Anusha
| Conduct Kick off Meeting | 07/21/23 - 01/10/24 | Sowmya Mutya & Lakshmi Anusha
| Research and Select Virtual Event Platform | 07/21/23 - 08/04/23 | Anyass Ibrahim & Isaac Kwame Duah
| Finalize Panel Discussion and Presentation Topics | 07/28/23 - 08/10/23 | Isaac Kwame Duah
| Allocate Budget for each Phase | 07/24/23 - 08/16/23 | Jair Greene & Anyass Ibrahim
Event Execution |  | 08/11/23 - 11/13/23 | Sai Goutham Chedhella & Anyass Ibrahim
| Setup Virtual Event Platform | 08/14/23 - 09/15/23 | Anyass Ibrahim & Isaac Kwame Duah
| Train Team Members and Speakers on the Platform | 08/24/23 - 10/19/23 | Renee Ashby & Mohammad Adul Gafoor
| Launch Marketing Campaigns | 09/15/23 - 01/09/24 | Sai Goutham Chedhella & Mohammad Adul Gafoor
| Conduct Panel Discussions and Presentations | 09/20/23 - 11/17/23 | Sowmya Mutya, Lakshmi Anusha & Isaac Kwame Duah
| Organize Interactive Activities | 09/20/23 - 12/29/23 | Sowmya Mutya, Lakshmi Anusha & Sai Goutham Chedhella
| Assess and Mitigate Risks | 08/08/23 - 01/04/24 | Sowmya Mutya, Lakshmi Anusha & Anyass Ibrahim
Post Event Activites and Project Closure |  | 12/11/23 - 01/11/24 | Sowmya Mutya, Lakshmi Anusha & Emmanuel Eze
| Create Post Event Report | 07/19/23 - 01/01/24 | Sowmya Mutya, Lakshmi Anusha & Emmanuel Eze
| Follow up with Attendees | 12/28/23 - 01/09/24 | Emmanuel Eze
Celebrate Success and thank the team | Celebrate Success and thank the team | 01/10/24 - 01/11/24 | Sowmya Mutya & Lakshmi Anusha