## Sheet1
Project Deliverable | Project Manager | Event Coordinator | Content Curator | Marketing + Communication Specialist | Technical Support Team | Design Team | Budget Manager | Evaluation and Feedback Analyst
Pre Event Planning + Setup | R | A | R | I | I | C | A | I
Define Project Scope and Objectives | R | I | I | C | R | C | I | I
Assemble Project Team | R | I | A | I | C | I | I | I
Conduct kick off Meeting | R | I | C | I | C | C | A | I
Research and Select Virtual Event Platform | I | I | A | C | R | R | I | I
Finalize Panel Discussion and Presentation Topics | A | I | C | I | I | R | I | C
Allocate Budget for each Phase | A | C | I | I | I | I | R | I
Event Execution | A | R | C | C | R | C | I | C
Setup Virtual Event Platform | A | I | C | I | R | R | I | I
Train Team Members and Speakers on the Platform | A | I | R | R | I | C | I | I
Launch Marketing Campaigns | A | R | I | R | I | C | I | I
Conduct Panel Discussions and Presentations | R | A | C | C | I | R | I | I
Organize Interactive Activities | R | R | C | C | I | C | I | I
Assess and Mitigate Risks | R | I | C | I | R | I | A | I
Post Event Activities and Project Closure | R | C | A | I | C | I | C | R
Create Post Event Report | R | C | C | I | I | I | A | R
Follow up with Attendees | I | I | I | C | I | I | I | R
Celebrate Success and thank the team | R | A | C | I | I | I | I | I
Legend
|  | R - | Responsible
|  | A - | Accountable
|  | C - | Consulted
|  | I - | Informed