## Three-Point Project Cost Est.
Project Title: |  |  |  |  | RUNNING WEIGHTED AVERAGE TOTAL: |  | 59966.6667
DETAILS |  |  |  | COST ESTIMATE SCENARIOS |  |  | WEIGHTED AVERAGE | ADDITIONAL INFORMATION / NOTES
DATE | WBS ID (Corresponding to WBS tasks) | ITEM / TASK DESCRIPTION | GATHERED BY (Who is responsible) | BEST-CASE | MOST LIKELY / REALISTIC | WORST-CASE
07/10/23 - 08/10/23 | 1.1 | Pre Event Planning Setup | Sowmya Mutya, Lakshmi Anusha & Renee Ashby | 9000 | 11000 | 14000 | 11166.6667
7/11/23 - 07/18/23 | 1.1.1 | define Project Scope and Objectives | Sowmya Mutya, Lakshmi Anusha & Anyass Ibrahim | 500 | 800 | 1200 | 816.6667
07/10/23 - 07/15/23 | 1.1.2 | Assemble Project Team | Sowmya Mutya & Lakshmi Anusha | 1000 | 1500 | 1800 | 1466.6667
07/21/23 - 01/10/24 | 1.1.3 | Conduct Kick-off Meeting | Sowmya Mutya & Lakshmi Anusha | 300 | 500 | 1000 | 550
07/21/23 - 08/04/23 | 1.1.3.1 | Research and Select Virtual Event Platform | Anyass Ibrahim & Isaac Kwame Duah | 3200 | 4000 | 5000 | 4033.3333
07/28/23 - 08/10/23 | 1.1.3.2 | Finalize Panel Discussion and Presentation Topics | Isaac Kwame Duah | 800 | 1000 | 1500 | 1050
07/24/23 - 08/16/23 | 1.1.3.3 | Allocate Budget for Each Phase | Jair Greene & Anyass Ibrahim | 3000 | 3200 | 3500 | 3216.6667
08/11/23-11/13/23 | 1.2 | Event Execution | Sai Goutham Chedhella & Anyass Ibrahim | 11000 | 14000 | 16000 | 13833.3333
08/14/23 - 09/15/23 | 1.2.1 | Set up Virtual Event Platform | Anyass Ibrahim & Isaac Kwame Duah | 400 | 500 | 700 | 516.6667
08/24/23 -10/19/23 | 1.2.2 | Train Team Members and Speakers on Platform | Renee Ashby & Mohammad Adul Gafoor | 4000 | 5500 | 5800 | 5300
09/15/23 - 01/09/24 | 1.2.3 | Launch Meeting Campaigns | Sai Gotham Chedhella & Mohammad Adul Gafoor | 1500 | 2000 | 2800 | 2050
09/20/23-11/17/23 | 1.2.3.1 | Conduct Panel Discussions and Presentations | Sowmya Mutya, Lakshmi Anusha & Isaac Kwame Duah | 1000 | 1200 | 1500 | 1216.6667
09/20/23-12/29/23 | 1.2.3.2 | Organize Interactive Activities | Sowmya Mutya, Lakshmi Anusha & Sai Goutham Chedhella | 1500 | 1800 | 2000 | 1783.3333
08/08/23-01/04/24 | 1.2.3.3 | Assess and Mitigate Risk | Sowmya Mutya, Lakshmi Anusha & Anyass Ibrahim | 2600 | 3000 | 3200 | 2966.6667
12/11/23-/01/11/24 | 1.3 | Post Event Activities and Project Closure | Sowmya Mutya, Lakshmi Anusha & Emmanuel Eze | 4000 | 5000 | 6000 | 5000
07/19/23-01/01/24 | 1.3.1 | Create Post Event Report | Sowmya Mutya, Lakshmi Anusha & Emmanuel Eze | 1800 | 2000 | 2200 | 2000
12/28/23-01/09/24 | 1.3.2 | Follow up with Attendees | Emmanuel Eze | 700 | 1000 | 1300 | 1000
01/10/24-01/11/24 | 1.3.3 | Celebrate Success and thank the team | Sowmya Mutya, Lakshmi Anusha | 1500 | 2000 | 2500 | 2000
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 47800 | 60000 | 72000 | 59966.6667
Final Estimate