## Risk log
Risk Register
Project name:
Project manager(s):
[Text in red and enclosed in [ ] is explanatory and should be deleted]
ID | Date raised | Risk description | Likelihood | Impact | Severity | Proximuty | Owner | Mitigating action | Contingent action | Progress on actions | Status
[1] | [12/12/2015] | purpose and project need in not well defined | Medium | High | [High] | This indicates when the idea present we start solving problen statements of the idea. | [project sponser] | Develop a detailed research on the idea and problen statements. | Implement the backup plan if the resource is also available.As inovating new thoughts | [80% completed. Update within 12/03/2015 ] | [Closed]
[2] |  | Budget overrun | Medium | High | [High] | This indicates when the risk may occur and can be used to schedule risk mitigation activities. | [project manager] | Develop a detailed budget and track expenses regularly. | Implement the backup plan if the resource is also available.As inovating new thoughts | [80% completed. Update within 12/03/2015 ] | [Open]
[3] |  | Venue availability issues | Low | Meadium | [Low] | Book the venue well in advance and have backup options identified. | [project Manager] | Negotiate a flexible contract to accommodate potential changes. | Implement the backup plan if the resource is also available.As inovating new thoughts | [80% completed. Update within 12/03/2015 ] | [Waiting]
[4] |  | Technology failures | Meadium | Meadium | [High] | Conduct thorough testing of all technological aspects before the event. | [Project Manager] | Have technical support on standby during the event. | Implement the backup plan if the team unable to complete full task we can take technologies as rent. | [100% completed] | [Closed]
[5] |  | Travel restrictions (due to unforeseen circumstances) | High | High | [Low] | Develop a contingency plan for remote participation. | [Project Scribe] | virtual attendance if physical attendance is restricted. | Implement the backup plan if the team unable to attend hybrid. | [100% completed] | [Closed]
[6] |  | Inadequate volunteer/staff | Medium | Low | [Low] | Recruit and train additional volunteers/staff to cover potential gaps. | [Project Lead] | We can assist any participants to go as volunteers. | Implement the backup plan if the team unable to attend hybrid. | [100% completed] | [Closed]
[7] |  | Cultural misunderstandings | Low | Meadium | [Low] | Cultural sensitivity training | [Project Scribe] | Provide cultural sensitivity training to team members and communicate expectations clearly. | Implement the backup plan if the team unable to communicate. | [100% completed] | [Closed]
[8] |  | Marketing and promotion challenges | Meadium | High | [High] | Develop a comprehensive marketing strategy to achive targets | [project manager] | Develop a comprehensive marketing strategy and monitor its effectiveness regularly. | Be prepared to adjust tactics as needed. | [50% completed] | [Open]
[Notes
Every organisation has a different approach to the risk log. This example includes all of the information that needs to captured,
and has been used on numerous real world projects. However, feel free to tweak this to fit your project.]
[Columns you might want to add:
| Raised by | Who identified the risk.
| Closed date | The date the risk was closed.
| Last update | The date that the risk entry was last updated. Useful for ensuring that mitigating actions are put in place.
| Action by | This field can be used to differentiate between the person accountable for managing this risk and the person
actually carrying out the mitigating actions.]

## Severity Table
Severity table or Risk Matrix
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High
Alternative Severity Tables
4 by 4 Risk Matrix
5 by 5 risk matrix - aviation example